ReceiptSnap

Implementation Plan

Test-Driven Development  •  Trunk-Based Git  •  GitHub Actions CI

Version 1.0  |  March 2026  |  Phase 1 MVP

2–5 hrs/week  |  Estimated duration: 14–18 weeks

# 1. Plan Overview

This document defines the sprint-by-sprint implementation plan for ReceiptSnap Phase 1. Development follows a strict Test-Driven Development (TDD) cycle, trunk-based version control on Git, and automated test runs via GitHub Actions on every push to main.

Given a part-time schedule of 2–5 hours per week, the plan is broken into 7 focused sprints. Each sprint has a single clear deliverable, a set of TDD tasks ordered Red → Green → Refactor, and an explicit Definition of Done checklist that must be fully satisfied before moving to the next sprint.

# 2. TDD Approach

## 2.1  The Red → Green → Refactor Cycle

Every feature in ReceiptSnap is built using the following strict TDD cycle. No production code is written before a failing test exists.

| Phase | Git Commit Prefix | What You Do |
| --- | --- | --- |
| 🔴 Red | test: | Write a test for the behaviour you want. Run it — it must FAIL. If it passes without code changes, the test is wrong. |
| 🟢 Green | feat: | Write the minimum production code needed to make the test pass. No extras. Run tests — all must pass. |
| 🔵 Refactor | refactor: | Clean up the code without changing behaviour. Extract functions, rename for clarity, remove duplication. Tests must still pass after every change. |

## 2.2  Testing Stack

- Jest — unit tests for all service modules (csvSerializer, validator, expenseNumberGen, storageService, config)

- React Native Testing Library (RNTL) — component and screen tests; render, interact, assert without a device

- GitHub Actions — runs jest --coverage on every push to main; blocks merge if any test fails or coverage drops below threshold

- No Detox / E2E in Phase 1 — manual smoke testing on device is sufficient given the solo team size

## 2.3  Coverage Policy

The following minimum coverage thresholds are enforced in jest.config.ts and checked by GitHub Actions:

jest.config.ts — coverage thresholds

coverageThreshold: {

global: {

branches:   80,   // All if/else paths

functions:  90,   // All exported functions

lines:      85,   // All executable lines

statements: 85,

},

// Service layer must be fully covered

'./src/services/': {

branches:   100,

functions:  100,

lines:      100,

statements: 100,

},

}

## 2.4  Trunk-Based Git Workflow

All development happens on main. Short-lived work-in-progress commits are allowed as long as tests pass before pushing. The commit message convention follows Conventional Commits:

Commit message format

test: write failing test for csvSerializer header row          ← Red

feat: implement csvSerializer serialize() function             ← Green

refactor: extract escapeCell helper in csvSerializer           ← Refactor

Other prefixes used in this project:

chore:   project setup, config, dependencies

ci:      GitHub Actions workflow changes

fix:     bug fixes (always write a regression test first)

docs:    documentation only

Rule: never push to main with failing tests. Run npm test before every push. GitHub Actions is the safety net, not the first line of defence.

# 3. GitHub Actions CI Pipeline

A single workflow file handles all automated checks on every push to main. It runs in under 2 minutes on a standard GitHub-hosted runner.

.github/workflows/ci.yml

name: CI

on:

push:

branches: [main]

jobs:

test:

runs-on: ubuntu-latest

steps:

- uses: actions/checkout@v4

- uses: actions/setup-node@v4

with:

node-version: 20

cache: npm

- name: Install dependencies

run: npm ci

- name: Type check

run: npx tsc --noEmit

- name: Run tests with coverage

run: npm test -- --coverage --ci

- name: Upload coverage report

uses: actions/upload-artifact@v4

with:

name: coverage-report

path: coverage/

The pipeline enforces three gates in order: TypeScript type check → Jest tests → Coverage thresholds. A failure at any gate fails the entire run and is visible on the GitHub commit status.

# 4. Sprint Timeline Summary

Total estimated duration at 2–5 hrs/week is 14–18 weeks. Sprints are time-boxed to 2 weeks each. If a sprint overruns, tasks carry forward — the Definition of Done gate must still be met before progressing.

| Sprint | Focus | Key Deliverable | Effort | TDD Gate |
| --- | --- | --- | --- | --- |
| S1 | Project Foundation | Expo app boots, CI green | 2–4 hrs | CI pipeline passing |
| S2 | Config + Types | Config & types fully tested | 3–5 hrs | 100% service coverage |
| S3 | Storage Service | Queue persists across restarts | 4–6 hrs | 100% service coverage |
| S4 | Business Logic | CSV + validation + exp. numbers | 5–8 hrs | 100% service coverage |
| S5 | Queue State | Context + hooks fully tested | 4–6 hrs | 90%+ hook coverage |
| S6 | UI Screens | All screens render + interact | 6–10 hrs | 80%+ component coverage |
| S7 | Integration + Polish | Full flow works end-to-end | 4–6 hrs | All DoD items checked |

SPRINT 1  —  Project Foundation & CI Setup

Duration: Weeks 1–2  |  Estimated effort: 2–4 hours

Goal: Get the Expo project scaffolded, TypeScript configured, Jest and RNTL installed, and GitHub Actions running. No app features yet — this sprint is entirely about the development environment being correct and the CI pipeline being green before a single line of feature code is written.

| # | Task | Type | TDD Phase | Files Involved |
| --- | --- | --- | --- | --- |
| S1-01 | Initialise Expo project with TypeScript template | Setup | — | app.json, tsconfig.json |
| S1-02 | Install Jest, RNTL, and jest-expo preset | Setup | — | package.json, jest.config.ts |
| S1-03 | Configure jest.config.ts with coverage thresholds | Setup | — | jest.config.ts |
| S1-04 | Write first smoke test — App renders without crashing | Test | Red → Green | __tests__/App.test.tsx |
| S1-05 | Create .github/workflows/ci.yml | CI/CD | — | .github/workflows/ci.yml |
| S1-06 | Push to main — verify CI pipeline goes green | CI/CD | — | GitHub Actions |
| S1-07 | Create .env with all EXPO_PUBLIC_ variables | Setup | — | .env, .env.example |
| S1-08 | Add .env to .gitignore; commit .env.example | Setup | — | .gitignore, .env.example |

Sprint 1 — Definition of Done

|  | Definition of Done — Checklist Item | Status |
| --- | --- | --- |
| 1 | Expo app launches on Android emulator without errors | [ ] |
| 2 | npm test runs and all tests pass locally | [ ] |
| 3 | GitHub Actions CI workflow exists and passes on push to main | [ ] |
| 4 | Coverage report is generated and uploaded as a CI artifact | [ ] |
| 5 | .env.example committed with all required variable names (no values) | [ ] |
| 6 | TypeScript type check passes with zero errors (tsc --noEmit) | [ ] |

SPRINT 2  —  Config Module + Core Types

Duration: Weeks 3–4  |  Estimated effort: 3–5 hours

Goal: Build and fully test the Config module and TypeScript types. These are the foundation everything else depends on. 100% test coverage required on src/constants/config.ts before moving on.

| # | Task | Type | TDD Phase | Files Involved |
| --- | --- | --- | --- | --- |
| S2-01 | Define Receipt and CSVRow interfaces in src/types/index.ts | Test | Red → Green | src/types/index.ts |
| S2-02 | Write tests for Config — each env var returns correct value | Test | Red | __tests__/config.test.ts |
| S2-03 | Write tests for Config — fallback values when env vars missing | Test | Red | __tests__/config.test.ts |
| S2-04 | Implement src/constants/config.ts to pass all Config tests | Implement | Green | src/constants/config.ts |
| S2-05 | Write tests for categories.ts — list is non-empty, all strings | Test | Red → Green | src/constants/categories.ts |
| S2-06 | Write tests for paymentTypes.ts — list is non-empty, all strings | Test | Red → Green | src/constants/paymentTypes.ts |
| S2-07 | Refactor config.ts — ensure types are strict (no any) | Refactor | Refactor | src/constants/config.ts |
| S2-08 | Confirm CI passes with 100% coverage on src/constants/ | CI/CD | — | GitHub Actions |

Sprint 2 — Sample Test Pattern (Red phase)

__tests__/config.test.ts

import { Config } from '../src/constants/config';

describe('Config', () => {

it('reads TAX_NAME from env', () => {

process.env.EXPO_PUBLIC_TAX_NAME = 'BC GST';

expect(Config.taxName).toBe('BC GST');

});

it('falls back to BC GST when TAX_NAME is not set', () => {

delete process.env.EXPO_PUBLIC_TAX_NAME;

// Re-import to force re-evaluation

jest.resetModules();

const { Config } = require('../src/constants/config');

expect(Config.taxName).toBe('BC GST');

});

it('parses TAX_RATE as a number', () => {

process.env.EXPO_PUBLIC_TAX_RATE = '5';

expect(typeof Config.taxRate).toBe('number');

expect(Config.taxRate).toBe(5);

});

});

Sprint 2 — Definition of Done

|  | Definition of Done — Checklist Item | Status |
| --- | --- | --- |
| 1 | Receipt and CSVRow TypeScript interfaces defined and exported | [ ] |
| 2 | Config module has 100% branch, function, and line coverage | [ ] |
| 3 | Fallback values tested for every Config property | [ ] |
| 4 | categories.ts and paymentTypes.ts have tests | [ ] |
| 5 | CI pipeline green with coverage thresholds met | [ ] |

SPRINT 3  —  Storage Service

Duration: Weeks 5–6  |  Estimated effort: 4–6 hours

Goal: Build and fully test storageService.ts and expenseNumberGen.ts. These are the only modules that touch AsyncStorage. They must be 100% covered with mocked storage calls — no real AsyncStorage in unit tests.

| # | Task | Type | TDD Phase | Files Involved |
| --- | --- | --- | --- | --- |
| S3-01 | Mock @react-native-async-storage/async-storage in jest setup | Setup | — | jest.setup.ts |
| S3-02 | Write tests: saveQueue serialises Receipt[] to JSON string | Test | Red | __tests__/storageService.test.ts |
| S3-03 | Write tests: loadQueue deserialises JSON back to Receipt[] | Test | Red | __tests__/storageService.test.ts |
| S3-04 | Write tests: loadQueue returns [] when storage is empty | Test | Red | __tests__/storageService.test.ts |
| S3-05 | Write tests: clearQueue removes queue key from storage | Test | Red | __tests__/storageService.test.ts |
| S3-06 | Implement storageService.ts to pass all storage tests | Implement | Green | src/services/storageService.ts |
| S3-07 | Write tests: loadCounter returns 1000 on first run | Test | Red | __tests__/storageService.test.ts |
| S3-08 | Write tests: saveCounter persists integer value | Test | Red | __tests__/storageService.test.ts |
| S3-09 | Write tests: expenseNumberGen returns EXP-1001 on first call | Test | Red | __tests__/expenseNumberGen.test.ts |
| S3-10 | Write tests: expenseNumberGen increments on each call | Test | Red | __tests__/expenseNumberGen.test.ts |
| S3-11 | Write tests: expenseNumberGen uses Config.expensePrefix | Test | Red | __tests__/expenseNumberGen.test.ts |
| S3-12 | Implement expenseNumberGen.ts to pass all tests | Implement | Green | src/services/expenseNumberGen.ts |
| S3-13 | Refactor both services — extract storage key constants | Refactor | Refactor | src/services/storageService.ts |

Sprint 3 — Sample Test Pattern (mocking AsyncStorage)

__tests__/storageService.test.ts

import AsyncStorage from '@react-native-async-storage/async-storage';

import { saveQueue, loadQueue } from '../src/services/storageService';

import { Receipt } from '../src/types';

// AsyncStorage is auto-mocked via jest.setup.ts

const mockReceipts: Receipt[] = [

{ id: '1', vendor: 'Staples', amount: 45.67, date: '2026-03-01',

category: 'Office Supplies', expenseNumber: 'EXP-1001',

notes: '', taxName: 'BC GST', taxRate: 5,

paymentType: 'Credit Card', imageUri: 'file://test.jpg', createdAt: 0 }

];

describe('storageService', () => {

beforeEach(() => jest.clearAllMocks());

it('saveQueue calls AsyncStorage.setItem with serialised JSON', async () => {

await saveQueue(mockReceipts);

expect(AsyncStorage.setItem).toHaveBeenCalledWith(

'receipt_queue',

JSON.stringify(mockReceipts)

);

});

it('loadQueue returns parsed receipts from storage', async () => {

(AsyncStorage.getItem as jest.Mock).mockResolvedValue(

JSON.stringify(mockReceipts)

);

const result = await loadQueue();

expect(result).toEqual(mockReceipts);

});

it('loadQueue returns [] when nothing is stored', async () => {

(AsyncStorage.getItem as jest.Mock).mockResolvedValue(null);

const result = await loadQueue();

expect(result).toEqual([]);

});

});

Sprint 3 — Definition of Done

|  | Definition of Done — Checklist Item | Status |
| --- | --- | --- |
| 1 | AsyncStorage is mocked in jest.setup.ts — no real storage calls in any test | [ ] |
| 2 | storageService.ts has 100% coverage across all 4 operations | [ ] |
| 3 | expenseNumberGen.ts has 100% coverage including prefix config | [ ] |
| 4 | Counter correctly increments across sequential calls in tests | [ ] |
| 5 | CI pipeline green | [ ] |

SPRINT 4  —  Business Logic — Validator + CSV Serializer

Duration: Weeks 7–9  |  Estimated effort: 5–8 hours

Goal: Build and fully test validator.ts and csvSerializer.ts. These are pure functions with no dependencies on React or storage — the easiest modules to achieve 100% coverage on. This sprint is the TDD sweet spot.

| # | Task | Type | TDD Phase | Files Involved |
| --- | --- | --- | --- | --- |
| S4-01 | Write tests: validator rejects empty vendor name | Test | Red | __tests__/validator.test.ts |
| S4-02 | Write tests: validator rejects amount <= 0 | Test | Red | __tests__/validator.test.ts |
| S4-03 | Write tests: validator rejects invalid date format | Test | Red | __tests__/validator.test.ts |
| S4-04 | Write tests: validator rejects category not in allowed list | Test | Red | __tests__/validator.test.ts |
| S4-05 | Write tests: validator returns valid=true for correct receipt | Test | Red | __tests__/validator.test.ts |
| S4-06 | Write tests: validator returns all errors simultaneously (not fail-fast) | Test | Red | __tests__/validator.test.ts |
| S4-07 | Implement validator.ts to pass all validation tests | Implement | Green | src/services/validator.ts |
| S4-08 | Write tests: serialize() produces correct CSV header row | Test | Red | __tests__/csvSerializer.test.ts |
| S4-09 | Write tests: serialize() maps all 9 fields to correct columns | Test | Red | __tests__/csvSerializer.test.ts |
| S4-10 | Write tests: serialize() formats amount to 2 decimal places | Test | Red | __tests__/csvSerializer.test.ts |
| S4-11 | Write tests: serialize() escapes commas inside vendor names | Test | Red | __tests__/csvSerializer.test.ts |
| S4-12 | Write tests: serialize() escapes double-quotes in notes field | Test | Red | __tests__/csvSerializer.test.ts |
| S4-13 | Write tests: serialize() handles empty receipts array → header only | Test | Red | __tests__/csvSerializer.test.ts |
| S4-14 | Implement csvSerializer.ts to pass all serializer tests | Implement | Green | src/services/csvSerializer.ts |
| S4-15 | Refactor validator — extract isValidDate() as testable helper | Refactor | Refactor | src/services/validator.ts |

Sprint 4 — Sample Test Pattern (CSV edge cases)

__tests__/csvSerializer.test.ts

import { serialize } from '../src/services/csvSerializer';

import { Receipt } from '../src/types';

const base: Receipt = {

id: '1', imageUri: 'file://x.jpg', createdAt: 0,

date: '2026-03-01', amount: 45.67, vendor: 'Staples',

category: 'Office Supplies', expenseNumber: 'EXP-1001',

notes: 'Printer paper', taxName: 'BC GST', taxRate: 5,

paymentType: 'Credit Card',

};

describe('csvSerializer', () => {

it('produces the correct header row', () => {

const csv = serialize([]);

const header = csv.split('\n')[0];

expect(header).toBe(

'date,amount,vendor,category,expense_number,notes,tax_name,tax_rate,payment_type'

);

});

it('formats amount to 2 decimal places', () => {

const csv = serialize([{ ...base, amount: 10 }]);

expect(csv).toContain(',10.00,');

});

it('wraps vendor in quotes when it contains a comma', () => {

const csv = serialize([{ ...base, vendor: 'Smith, Jones Ltd' }]);

expect(csv).toContain('"Smith, Jones Ltd"');

});

it('escapes double-quotes in notes', () => {

const csv = serialize([{ ...base, notes: 'He said "hello"' }]);

expect(csv).toContain('"He said ""hello"""');

});

});

Sprint 4 — Definition of Done

|  | Definition of Done — Checklist Item | Status |
| --- | --- | --- |
| 1 | validator.ts has 100% branch coverage — every error condition tested | [ ] |
| 2 | All validation errors are returned simultaneously, not just the first one | [ ] |
| 3 | csvSerializer.ts has 100% coverage — all 9 fields, all edge cases | [ ] |
| 4 | CSV output for a sample receipt matches the exact Invoice Ninja format | [ ] |
| 5 | Empty array input produces header-only CSV without crashing | [ ] |
| 6 | CI pipeline green with all coverage thresholds met | [ ] |

SPRINT 5  —  Queue State — Context + Hooks

Duration: Weeks 10–11  |  Estimated effort: 4–6 hours

Goal: Build and test QueueContext and all custom hooks. Tests use RNTL's renderHook utility to test hooks in isolation without mounting full screens.

| # | Task | Type | TDD Phase | Files Involved |
| --- | --- | --- | --- | --- |
| S5-01 | Write tests: QueueContext initialises with empty receipts + isLoading=true | Test | Red | __tests__/QueueContext.test.tsx |
| S5-02 | Write tests: HYDRATE action populates receipts and sets isLoading=false | Test | Red | __tests__/QueueContext.test.tsx |
| S5-03 | Write tests: ADD action appends receipt to queue | Test | Red | __tests__/QueueContext.test.tsx |
| S5-04 | Write tests: UPDATE action replaces receipt by id | Test | Red | __tests__/QueueContext.test.tsx |
| S5-05 | Write tests: DELETE action removes receipt by id | Test | Red | __tests__/QueueContext.test.tsx |
| S5-06 | Write tests: CLEAR_ALL action empties the queue | Test | Red | __tests__/QueueContext.test.tsx |
| S5-07 | Implement QueueContext.tsx with reducer to pass all tests | Implement | Green | src/context/QueueContext.tsx |
| S5-08 | Write tests: useQueue.addReceipt dispatches ADD with new Receipt | Test | Red | __tests__/useQueue.test.ts |
| S5-09 | Write tests: useQueue.deleteReceipt dispatches DELETE with id | Test | Red | __tests__/useQueue.test.ts |
| S5-10 | Write tests: useQueue.updateReceipt dispatches UPDATE | Test | Red | __tests__/useQueue.test.ts |
| S5-11 | Implement useQueue.ts hook to pass all hook tests | Implement | Green | src/hooks/useQueue.ts |
| S5-12 | Write tests: useImagePicker returns array of URIs on success | Test | Red | __tests__/useImagePicker.test.ts |
| S5-13 | Write tests: useImagePicker returns [] when user cancels | Test | Red | __tests__/useImagePicker.test.ts |
| S5-14 | Implement useImagePicker.ts with mocked expo-image-picker | Implement | Green | src/hooks/useImagePicker.ts |
| S5-15 | Write tests: useExport calls serialize then writes file then shares | Test | Red | __tests__/useExport.test.ts |
| S5-16 | Implement useExport.ts with mocked expo-file-system + expo-sharing | Implement | Green | src/hooks/useExport.ts |
| S5-17 | Verify persistence side-effect: context writes to storageService on change | Test | Red → Green | __tests__/QueueContext.test.tsx |

Sprint 5 — Sample Test Pattern (renderHook)

__tests__/useQueue.test.ts

import { renderHook, act } from '@testing-library/react-native';

import { useQueue } from '../src/hooks/useQueue';

import { QueueProvider } from '../src/context/QueueContext';

import React from 'react';

const wrapper = ({ children }: { children: React.ReactNode }) => (

<QueueProvider>{children}</QueueProvider>

);

describe('useQueue', () => {

it('starts with an empty queue', () => {

const { result } = renderHook(() => useQueue(), { wrapper });

expect(result.current.receipts).toEqual([]);

});

it('addReceipt appends a new item to the queue', async () => {

const { result } = renderHook(() => useQueue(), { wrapper });

await act(async () => {

await result.current.addReceipt('file://photo.jpg');

});

expect(result.current.receipts).toHaveLength(1);

expect(result.current.receipts[0].imageUri).toBe('file://photo.jpg');

});

it('deleteReceipt removes item by id', async () => {

const { result } = renderHook(() => useQueue(), { wrapper });

await act(async () => { await result.current.addReceipt('file://a.jpg'); });

const id = result.current.receipts[0].id;

await act(async () => { result.current.deleteReceipt(id); });

expect(result.current.receipts).toHaveLength(0);

});

});

Sprint 5 — Definition of Done

|  | Definition of Done — Checklist Item | Status |
| --- | --- | --- |
| 1 | All 6 reducer actions (HYDRATE, ADD, UPDATE, DELETE, CLEAR_ALL) tested | [ ] |
| 2 | Context persistence side-effect verified — storageService.saveQueue called on every mutation | [ ] |
| 3 | useQueue hook tested for all 4 operations | [ ] |
| 4 | useImagePicker tested for success and cancellation paths | [ ] |
| 5 | useExport tested with mocked file system and share sheet | [ ] |
| 6 | expo-image-picker and expo-file-system/expo-sharing are mocked in jest setup | [ ] |
| 7 | CI green with 90%+ hook/context coverage | [ ] |

SPRINT 6  —  UI — Screens & Components

Duration: Weeks 12–14  |  Estimated effort: 6–10 hours

Goal: Build and test all screens and components using React Native Testing Library. Tests focus on user-visible behaviour — what renders, what happens on tap, what gets called — not implementation details.

| # | Task | Type | TDD Phase | Files Involved |
| --- | --- | --- | --- | --- |
| S6-01 | Write tests: ReceiptCard renders vendor, date, amount, category | Test | Red | __tests__/ReceiptCard.test.tsx |
| S6-02 | Write tests: ReceiptCard calls onEdit when Edit tapped | Test | Red | __tests__/ReceiptCard.test.tsx |
| S6-03 | Write tests: ReceiptCard calls onDelete when Delete tapped | Test | Red | __tests__/ReceiptCard.test.tsx |
| S6-04 | Implement ReceiptCard.tsx to pass all card tests | Implement | Green | src/components/ReceiptCard.tsx |
| S6-05 | Write tests: ReceiptForm pre-fills taxName, taxRate, paymentType from Config | Test | Red | __tests__/ReceiptForm.test.tsx |
| S6-06 | Write tests: ReceiptForm pre-fills date with today | Test | Red | __tests__/ReceiptForm.test.tsx |
| S6-07 | Write tests: ReceiptForm shows validation errors on submit with empty fields | Test | Red | __tests__/ReceiptForm.test.tsx |
| S6-08 | Write tests: ReceiptForm calls onSubmit with correct data on valid input | Test | Red | __tests__/ReceiptForm.test.tsx |
| S6-09 | Implement ReceiptForm.tsx using react-hook-form | Implement | Green | src/components/ReceiptForm.tsx |
| S6-10 | Write tests: HomeScreen shows empty state when queue is empty | Test | Red | __tests__/HomeScreen.test.tsx |
| S6-11 | Write tests: HomeScreen renders a ReceiptCard per queue item | Test | Red | __tests__/HomeScreen.test.tsx |
| S6-12 | Write tests: HomeScreen Export button is disabled when queue is empty | Test | Red | __tests__/HomeScreen.test.tsx |
| S6-13 | Implement app/index.tsx (Home screen) | Implement | Green | app/index.tsx |
| S6-14 | Write tests: AddScreen calls pickFromCamera / pickFromGallery on tap | Test | Red | __tests__/AddScreen.test.tsx |
| S6-15 | Implement app/add.tsx (Add Receipt screen) | Implement | Green | app/add.tsx |
| S6-16 | Write tests: EntryScreen loads correct receipt by id from context | Test | Red | __tests__/EntryScreen.test.tsx |
| S6-17 | Implement app/entry/[id].tsx (Receipt Entry screen) | Implement | Green | app/entry/[id].tsx |
| S6-18 | Write tests: ReviewScreen renders all receipts with total amount | Test | Red | __tests__/ReviewScreen.test.tsx |
| S6-19 | Implement app/review.tsx (Review screen) | Implement | Green | app/review.tsx |
| S6-20 | Refactor screens — extract shared layout wrappers | Refactor | Refactor | app/_layout.tsx |

Sprint 6 — Sample Test Pattern (RNTL screen test)

__tests__/HomeScreen.test.tsx

import { render, screen } from '@testing-library/react-native';

import { QueueProvider } from '../src/context/QueueContext';

import HomeScreen from '../app/index';

import React from 'react';

const renderWithContext = (ui: React.ReactElement) =>

render(<QueueProvider>{ui}</QueueProvider>);

describe('HomeScreen', () => {

it('shows empty state message when queue has no receipts', () => {

renderWithContext(<HomeScreen />);

expect(screen.getByText(/no receipts yet/i)).toBeTruthy();

});

it('Export button is disabled when queue is empty', () => {

renderWithContext(<HomeScreen />);

const btn = screen.getByRole('button', { name: /export/i });

expect(btn.props.disabled).toBe(true);

});

});

Sprint 6 — Definition of Done

|  | Definition of Done — Checklist Item | Status |
| --- | --- | --- |
| 1 | ReceiptCard renders correctly and all callback props tested | [ ] |
| 2 | ReceiptForm pre-population from Config verified in tests | [ ] |
| 3 | ReceiptForm validation errors surface correctly — all fields covered | [ ] |
| 4 | HomeScreen empty state and populated state both tested | [ ] |
| 5 | Export button disabled state tested | [ ] |
| 6 | AddScreen camera and gallery paths both tested (with mocked image picker) | [ ] |
| 7 | EntryScreen loads receipt by ID correctly from context | [ ] |
| 8 | ReviewScreen shows correct totals | [ ] |
| 9 | CI green with 80%+ component/screen coverage | [ ] |

SPRINT 7  —  Integration, Polish & Release Prep

Duration: Weeks 15–18  |  Estimated effort: 4–6 hours

Goal: Wire everything together, write integration tests covering the full Add → Review → Export flow, perform manual smoke testing on a real Android device, and prepare for release. This sprint validates that all modules communicate correctly end-to-end.

| # | Task | Type | TDD Phase | Files Involved |
| --- | --- | --- | --- | --- |
| S7-01 | Write integration test: add 2 receipts → export → verify CSV output | Test | Red → Green | __tests__/integration/exportFlow.test.tsx |
| S7-02 | Write integration test: add receipt → delete → queue is empty | Test | Red → Green | __tests__/integration/queueFlow.test.tsx |
| S7-03 | Write integration test: app restart hydrates queue from storage | Test | Red → Green | __tests__/integration/persistence.test.tsx |
| S7-04 | Write regression test: editing a receipt does not duplicate it in queue | Test | Red → Green | __tests__/integration/queueFlow.test.tsx |
| S7-05 | Manual smoke test on Android device — full receipt capture to CSV export | Implement | — | Device testing |
| S7-06 | Manual smoke test on mobile Chrome browser — same flow | Implement | — | Browser testing |
| S7-07 | Fix any bugs found in smoke testing (write regression test first) | Implement | Red → Green | Various |
| S7-08 | Review all coverage reports — fill any gaps to meet thresholds | Implement | — | jest coverage report |
| S7-09 | Update .env.example with clear comments for all variables | Implement | — | .env.example |
| S7-10 | Write README.md — setup, run, test, build, export instructions | Implement | — | README.md |
| S7-11 | Build Android APK via expo build or EAS Build | Implement | — | eas.json |
| S7-12 | Tag v1.0.0 release on main — verify CI green on tag | CI/CD | — | GitHub Releases |

Sprint 7 — Sample Integration Test

__tests__/integration/exportFlow.test.tsx

// Full flow: add receipts → export → verify CSV content

import { renderHook, act } from '@testing-library/react-native';

import { useQueue } from '../../src/hooks/useQueue';

import { useExport } from '../../src/hooks/useExport';

import { QueueProvider } from '../../src/context/QueueContext';

import * as FileSystem from 'expo-file-system';

import React from 'react';

const wrapper = ({ children }: any) => <QueueProvider>{children}</QueueProvider>;

it('exports 2 receipts as valid CSV with correct headers', async () => {

const queue = renderHook(() => useQueue(), { wrapper });

const exporter = renderHook(() => useExport(), { wrapper });

await act(async () => {

await queue.result.current.addReceipt('file://r1.jpg');

await queue.result.current.addReceipt('file://r2.jpg');

});

await act(async () => {

await exporter.result.current.exportQueue(

queue.result.current.receipts

);

});

const written = (FileSystem.writeAsStringAsync as jest.Mock).mock.calls[0][1];

const lines = written.split('\n');

expect(lines[0]).toBe(

'date,amount,vendor,category,expense_number,notes,tax_name,tax_rate,payment_type'

);

expect(lines).toHaveLength(3); // header + 2 data rows

});

Sprint 7 — Definition of Done (Final Release Gate)

|  | Definition of Done — Checklist Item | Status |
| --- | --- | --- |
| 1 | All integration tests pass — add/edit/delete/export flows covered | [ ] |
| 2 | Regression test in place for receipt duplication bug (edit flow) | [ ] |
| 3 | App restart hydration integration test passes | [ ] |
| 4 | Manual smoke test passed on physical Android device | [ ] |
| 5 | Manual smoke test passed on Android Chrome mobile browser | [ ] |
| 6 | All jest coverage thresholds met — no threshold violations in CI | [ ] |
| 7 | README.md complete with setup, test, build, and export instructions | [ ] |
| 8 | .env.example committed with all variables and inline comments | [ ] |
| 9 | No TypeScript errors (tsc --noEmit passes) | [ ] |
| 10 | CI pipeline green on v1.0.0 tag | [ ] |
| 11 | Android APK built and installable | [ ] |

# 5. Regression & Bug Fix Policy

This policy applies throughout all sprints and must be followed any time a bug is discovered — whether found during development, smoke testing, or after release.

- Write a failing test that reproduces the bug exactly. Commit with prefix test: regression — do not fix the bug first.

- Fix the bug with the minimum change required. Commit with prefix fix:

- Confirm the regression test now passes. Push — CI must go green.

- Optionally refactor if the fix exposed structural issues. Commit with prefix refactor:

This guarantees that every bug that ever existed in the codebase has a permanent test preventing its return.

# 6. Developer Quick Reference

Daily development commands

# Run all tests (do this before every push)

npm test

# Run tests in watch mode during development

npm test -- --watch

# Run tests with coverage report

npm test -- --coverage

# Type check only (fast, no test run)

npx tsc --noEmit

# Run a single test file

npm test -- __tests__/csvSerializer.test.ts

# Start Expo dev server (Android)

npx expo start --android

# Start Expo dev server (Web)

npx expo start --web

End of Implementation Plan — v1.0

Do not advance to the next sprint until all Definition of Done items are checked.